## Tasks
task_id | task_name | duration | resource_requirements
1 | Project Kickoff | 2 | 1,1,0,0,0,0,0,0,0,0,0,0
2 | Requirement Analysis #1 | 4 | 1,0,0,2,0,0,0,0,0,0,0,1
3 | Requirement Analysis #2 | 5 | 1,0,0,2,0,0,0,0,0,0,0,1
4 | Requirement Analysis #3 | 4 | 1,0,0,2,0,0,0,0,0,0,0,1
5 | Requirement Analysis #4 | 5 | 1,0,0,2,0,0,0,0,0,0,0,1
6 | Requirement Analysis #5 | 4 | 1,0,0,2,0,0,0,0,0,0,0,1
7 | System Architecture | 4 | 0,1,3,0,0,0,0,0,0,0,0,0
8 | Data Model Design | 4 | 0,0,2,0,0,0,0,0,0,0,2,0
9 | API Spec Design | 4 | 0,0,2,0,0,1,0,0,0,0,0,0
10 | UI Prototype | 4 | 0,0,0,0,0,0,0,0,0,0,0,3
11 | Mobile UX Flow | 4 | 0,0,0,0,0,0,1,0,0,0,0,2
12 | Frontend Feature A | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
13 | Frontend Feature B | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
14 | Frontend Feature C | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
15 | Frontend Feature D | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
16 | Frontend Feature E | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
17 | Frontend Feature F | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
18 | Frontend Feature G | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
19 | Frontend Feature H | 5 | 0,0,0,0,4,0,0,0,0,0,0,1
20 | Backend Service A | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
21 | Backend Service B | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
22 | Backend Service C | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
23 | Backend Service D | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
24 | Backend Service E | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
25 | Backend Service F | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
26 | Backend Service G | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
27 | Backend Service H | 6 | 0,0,0,0,0,4,0,0,0,0,0,0
28 | Mobile Module A | 5 | 0,0,0,0,0,0,3,0,0,0,0,1
29 | Mobile Module B | 5 | 0,0,0,0,0,0,3,0,0,0,0,1
30 | Mobile Module C | 5 | 0,0,0,0,0,0,3,0,0,0,0,1
31 | Mobile Module D | 5 | 0,0,0,0,0,0,3,0,0,0,0,1
32 | Mobile Module E | 5 | 0,0,0,0,0,0,3,0,0,0,0,1
33 | Mobile Module F | 5 | 0,0,0,0,0,0,3,0,0,0,0,1
34 | ETL Pipeline | 5 | 0,0,0,0,0,1,0,0,0,0,3,0
35 | Data Warehouse Setup | 5 | 0,0,0,0,0,1,0,0,0,0,3,0
36 | Analytics Dashboard | 5 | 0,0,0,0,0,1,0,0,0,0,3,0
37 | Data Quality Checks | 5 | 0,0,0,0,0,1,0,0,0,0,3,0
38 | Frontend-Backend Integration | 4 | 0,0,0,0,2,2,0,0,2,0,0,0
39 | Mobile-Backend Integration | 4 | 0,0,0,0,2,2,0,0,2,0,0,0
40 | Data Integration | 4 | 0,0,0,0,2,2,0,0,2,0,0,0
41 | End-to-End Assembly | 4 | 0,0,0,0,2,2,0,0,2,0,0,0
42 | Unit Tests | 3 | 0,0,0,0,0,0,0,4,0,0,0,0
43 | Integration Tests | 4 | 0,0,0,0,0,0,0,3,0,1,0,0
44 | Performance Tests | 4 | 0,0,0,0,0,0,0,3,1,0,0,0
45 | Security Tests | 4 | 0,0,0,0,0,0,0,2,0,2,0,0
46 | User Acceptance Tests | 4 | 1,0,0,0,0,0,0,3,0,0,0,0
47 | Bug Fix Round | 4 | 0,0,0,0,2,2,0,2,0,0,0,0
48 | Infrastructure Provisioning | 3 | 0,0,0,0,0,0,0,0,3,0,0,0
49 | Staging Deployment | 2 | 0,0,0,0,0,0,0,0,2,1,0,0
50 | Production Deployment | 1 | 0,1,0,0,0,0,0,0,2,1,0,0
51 | Post-Deployment Monitoring | 3 | 0,0,0,0,0,0,0,2,1,0,0,0
52 | Project Retrospective | 2 | 1,2,0,0,0,0,0,0,0,0,0,0
53 | Documentation Finalization | 3 | 0,0,0,1,0,0,0,0,0,0,0,1
54 | Marketing Launch | 2 | 1,0,0,0,0,0,0,0,0,0,0,2

## Resources
resource_id | resource_name | capacity
0 | Product Owners | 3
1 | Project Managers | 4
2 | Architects | 4
3 | Business Analysts | 5
4 | Frontend Developers | 12
5 | Backend Developers | 12
6 | Mobile Developers | 6
7 | QA Engineers | 10
8 | DevOps Engineers | 5
9 | Security Specialists | 3
10 | Data Engineers | 4
11 | UI/UX Designers | 5

## Dependencies
predecessor_id | successor_id
1 | 2
1 | 3
1 | 4
1 | 5
1 | 6
2 | 7
2 | 8
2 | 9
2 | 10
2 | 11
10 | 12
10 | 13
10 | 14
10 | 15
10 | 16
10 | 17
10 | 18
10 | 19
9 | 20
9 | 21
9 | 22
9 | 23
9 | 24
9 | 25
9 | 26
9 | 27
11 | 28
11 | 29
11 | 30
11 | 31
11 | 32
11 | 33
8 | 34
8 | 35
8 | 36
8 | 37
12 | 38
13 | 38
14 | 38
15 | 38
16 | 38
17 | 38
18 | 38
19 | 38
20 | 38
28 | 39
29 | 39
30 | 39
31 | 39
32 | 39
33 | 39
20 | 39
34 | 40
35 | 40
36 | 40
37 | 40
38 | 41
39 | 41
40 | 41
38 | 42
39 | 42
40 | 42
41 | 42
38 | 43
39 | 43
40 | 43
41 | 43
38 | 44
39 | 44
40 | 44
41 | 44
38 | 45
39 | 45
40 | 45
41 | 45
38 | 46
39 | 46
40 | 46
41 | 46
42 | 47
43 | 47
44 | 47
45 | 47
46 | 47
47 | 48
48 | 49
49 | 50
50 | 51
50 | 52
50 | 53
50 | 54
53 | 54