## Tasks
task_id | task_name | duration | resource_requirements
1 | Design | 5 | 2,1,0
2 | Procurement | 3 | 1,0,2
3 | Installation | 4 | 0,2,3
4 | Testing | 2 | 1,1,1
5 | Commissioning | 1 | 0,1,0

## Resources
resource_id | resource_name | capacity
0 | Engineers | 3
1 | Electricians | 4
2 | Technicians | 5

## Dependencies
predecessor_id | successor_id
1 | 2
2 | 3
3 | 4
4 | 5